## Лист1
Tasks | Description | № | Members | Start Time | End time
Problem Analysis and gathering information | Find information about our problem and analyse it for finding solution | 1 | Sattibay Galymzhan | 2020-10-06 | 2020-10-30
Create UML diagram for microservices | Create structure of our microservices and analyse interactive of services | 2 | Beibarys Tursynbek | 2020-10-30 | 2020-11-10
Create DB diagram. | Create DB diagram and analyse where it is stay. Create link between table. | 3 | Beibarys Tursynbek | 2020-11-10 | 2020-11-17
Back-end: Admin panel for database | Admin service | 4 | Sattibay Galymzhan | 2020-11-17 | 2020-11-27
Back-end: ACL endpoints | Preparing acl service, creating DB | 5 | Tazhben Arsu | 2020-11-27 | 2020-12-07
Front-end: ACL panel | ACL panel for roles, users | 6 | Beibarys Tursynbek | 2020-12-07 | 2020-12-14
Back-end: OAuth | Preparing service for issuing JWT and authentication | 7 | Sattibay Galymzhan | 2020-12-14 | 2020-12-25
Back-end: Web-socket streaming | research web-socket, developing servicefor streaming in java | 8 | Sattibay Galymzhan | 2020-12-25 | 2021-01-06
Front-end: Web-socket streaming | Developing front demonstration of stream | 9 | Tazhben Arsu | 2021-01-06 | 2021-02-15
Front-end: Main site | Developing front demonstration of stream | 10 | Tazhben Arsu | 2021-02-15 | 2021-03-15